Halo Holdings — Track B

HaloFlow — Product Decisions, Demo Scope & Development Estimate

Internal working document. Captures the decisions taken in the PMF and strategy review of 30–31 August 2026, defines the demo scope agreed there, and gives a development estimate grounded in the current state of the repository.

Version 1 — 31 August 2026. Companions: HaloFlow_Tier_UseCase_Roadmap_v4.docx and HaloFlow_Module_Delivery_Tracker.md.

# 1. Decisions Confirmed

| Decision | Detail |
| --- | --- |
| EMR-neutral roadmap | All references to a named EMR were removed from the roadmap in v4. The product targets EMRs common among independently owned clinics. See §2 on the relationship between this and the athenahealth adapter already in the codebase. |
| The bundle is the value proposition | Value comes from connecting the workflow end to end, not from any single feature. Overlap with what competitors already sell is accepted; the differentiation is assembly and operation. A partial solution is worth materially less than half of a complete one, so the target is the complete Phase 1 set rather than a single wedge. |
| Turnkey / done-for-you delivery | The clinic is assumed to have no IT support. HaloFlow performs setup, integration, configuration and support. Setup burden sits with HaloFlow, not the clinic. This is the deliberate answer to the segment being under-served. |
| Demo the whole, deliver in sequence | Clinics buy on the end state, so the demo shows the complete end-to-end workflow even where it runs on synthetic data. The build and the rollout proceed one module and one workflow at a time. Demo completeness and product completeness are deliberately decoupled. |
| Gradual onboarding, one workflow at a time | Avoids disrupting the clinic, and spreads HaloFlow’s own setup effort so no clinic needs several prerequisite tracks to complete at once. Each go-live is a trust checkpoint before the next ask. |
| Rollout order tiebreaker at each clinic | Prefer starting with the workflow whose external prerequisites are already met — for example, a clinic already on cloud fax. Fastest visible win. |
| A recommended default order is maintained | The order is agreed with each clinic, but HaloFlow recommends a standard default and deviates only for a stated reason. Rationale: per-clinic configuration drift is the main support-load risk for a small team. |
| Human approval gates are a selling point | Routine steps execute under clinic-approved rules; anything needing judgment goes to staff. Booking, refills and clinical-adjacent actions stay approval-gated. Customer materials should state this positively rather than describe the system as autonomous. |
| Business model | Bootstrapped, no outside investors sought. Slow, stable growth preferred over scale. High-touch delivery accepted as a deliberate trade, subject to the onboarding-cost measurement in §2. |

# 2. Open Decisions

| Open item | What is needed to close it |
| --- | --- |
| EMR selection — probably already decided in practice | The roadmap is now EMR-neutral, but the codebase contains a working athenahealth adapter (src/haloflow/ehr/athenahealth.py) built on athenahealth’s proprietary REST v1 rather than FHIR, chosen for transactional write-back coverage. In effect athenahealth is the first integration target. Two things follow. First, this should be written down as a decision rather than left implicit in code. Second, it is a defensible choice: athenahealth is common among independent practices and runs a public developer programme, which fits the target segment far better than the pilot clinic’s own EMR would. What remains to confirm: production API access terms and cost, whether each customer practice requires its own approval, and realistic onboarding time per practice. |
| Pilot clinic vs. target segment | The pilot clinic and the first integration target are not the same platform. That is acceptable, but it should be a conscious choice: the pilot proves the workflows and the compliance pattern, while the first sellable integration targets the segment the business intends to serve. Decide explicitly whether the pilot clinic is a design partner for learning or the first production customer — the two imply different work. |
| Onboarding cost vs. price | Turnkey delivery puts setup labour on HaloFlow. The decisive unit-economics question is how many hours it takes to onboard one clinic and whether a tiered subscription recovers that within an acceptable number of months. Measure it on the first clinic and record it; it is not knowable in advance. |
| Materials / roadmap consistency | Client and investor materials describe steps such as "AI books and confirms" as autonomous execution. The roadmap states booking is approval-gated and never autonomous. Align the materials to the roadmap; the approval gate is a selling point to a cautious clinical buyer, not a limitation to be hidden. |
| Materials emphasis vs. observed pain | The end-to-end diagram in the deck is scheduling- and eligibility-centric. The pain observed at the pilot clinic is phone, fax and paperwork volume. Consider giving fax and records work a visible place in the primary diagram. |
| Legacy prototype disposition | src/haloflow/modules/ contains first-pass implementations of all four Phase 1 workflows against athenahealth, Notifyre and Stedi, plus a scheduler. This code predates the M01 architecture, is outside CI lint/type scope, and carries 32 known Ruff findings. Decide explicitly whether it is (a) a reference spike to be read and discarded, or (b) code to be migrated behind M01. The tracker currently implies (b). The distinction materially changes the M07–M09 estimates. |

# 3. Demo Scope

The demo is both the sales asset and the discovery instrument. It is shown to local clinics well before the product is deployable, and their reactions are the first independent evidence about product-market fit.

## 3.1 Principles

- One continuous story, not four feature tours. A practice manager should recognise their own day. Separate feature demos make the viewer assemble the picture themselves — which is precisely the work HaloFlow claims to do for them.

- Show the destination, not just step one. The buying decision is made on the end state; the first workflow is only what they agree to start with.

- Synthetic data throughout. No PHI and no live integrations required. What is real and what is simulated is recorded in §3.3 and disclosed honestly if asked.

- Re-skinnable per prospect. Specialty, payer names and plausible local fax senders should be swappable so the demo does not read as built for somebody else.

- Include one deliberate failure. An ambiguous fax, or an eligibility response that does not parse, landing cleanly on a named person with full context attached. This demonstrates the safety model better than any slide and speaks to the objection a cautious owner-physician actually holds.

## 3.2 Scenario — “a day at the clinic”

| # | Beat | What is shown |
| --- | --- | --- |
| 1 | Patient request arrives | An inbound request is captured; intent and required details are extracted. |
| 2 | Coverage checked | Eligibility verified against the clinic’s common plans ahead of the visit; result recorded. |
| 3 | Appointment handled | A slot is proposed under the clinic’s rules and held pending; staff approve; the patient is confirmed automatically. |
| 4 | Reminder and confirmation | A confirmation request goes out on the approved timing and channel; the reply is captured without staff involvement. |
| 5 | Fax arrives and routes itself | An inbound document is identified, associated with the right patient and queue, and delivered to the right person with the ask made explicit. |
| 6 | Records request closes | An outgoing records package with auto-filled cover sheet, sent, with delivery confirmation logged. |
| 7 | Care gap surfaces | A patient due for a preventive measure is identified and contacted. |
| 8 | Exception lands on staff | The deliberate failure case. An item the system will not decide is escalated to a named person with the source document and context attached — visible, never suppressed. |
| 9 | Outcome recorded | Status and audit trail for everything above. |

## 3.3 Real versus simulated in the demo

| Component | Demo state | Note |
| --- | --- | --- |
| Document understanding / intent extraction | Real | Runs on synthetic documents. The capability most worth showing genuinely. |
| Rules engine and approval gates | Real | Core of the product story; should behave as it will in production. |
| Queue / staff review interface | Real | The surface staff will actually use. |
| EMR read and write-back | Simulated | Mock adapter over synthetic records, so the demo is not blocked on production API access. |
| Eligibility (clearinghouse) | Simulated | Canned payer responses, including one that fails to parse. |
| Fax send / receive | Simulated | Pre-loaded inbound documents; outbound rendered but not transmitted. |
| SMS delivery | Simulated | Rendered message threads; no live sending, so no messaging registration is needed for the demo. |
| Voice | Out of scope | Tier 3. May appear as a transcript if useful, but is not built for this milestone. |

## 3.4 What to observe in the room

- Which beat produces the strongest reaction — that is the workflow to start with at that clinic.

- Whether they describe their current process unprompted, and in what detail.

- What they say about the exception case. Trust in escalation is the gating concern for a clinical buyer.

- Whether they name their EMR, and what they already believe it does for them.

- Whether they ask about price, timeline, or who else uses it — each signals a different level of interest.

- Whether anyone volunteers volumes: faxes per day, no-show rate, eligibility checks per week. Volunteered numbers are far stronger evidence than agreement.

# 4. Delivery and Onboarding Model

Onboarding is incremental. Each workflow carries only its own external prerequisites, so no clinic waits on several paperwork tracks at once.

| Workflow | External prerequisites | Who does the work |
| --- | --- | --- |
| Incoming & outgoing faxes | Clinic fax must be digital (cloud/efax); fax vendor BAA | HaloFlow arranges. Migration required if the clinic is still on a physical machine. |
| Appointment reminders & no-shows | Messaging registration (A2P brand and campaign); patient consent policy; schedule access | HaloFlow registers and configures. |
| Insurance eligibility checks | Clearinghouse account and trading-partner enrolment per payer | HaloFlow prepares; clinic signature required on payer enrolment forms. |
| Preventive care & care-gap outreach | Payer care-gap list access; messaging registration (shared with reminders) | Clinic supplies payer files; HaloFlow ingests. |
| All workflows | BAA with the clinic; EMR access provisioning | HaloFlow drafts and arranges; clinic signs. |

The BAA with the clinic and the subprocessor BAA chain must be complete before any PHI is touched, regardless of pilot or free-trial status.

# 5. Current State of the Build

Observed in the repository on 31 August 2026. This section exists so the estimate in §6 is anchored to real progress rather than to scope alone.

| Area | State |
| --- | --- |
| Module plan | A twelve-module plan (M01–M12) with scope, dependencies and a recommended implementation order is documented in HaloFlow_Module_Delivery_Tracker.md. The build order is therefore already defined; this document does not restate or change it. |
| M01 — Tenant Context and Data Access | Design and ADR accepted; foundation merged (PR #1). Shared control schema and roles, resolver-issued tenant context, transaction gateway, per-statement capability checks, pool reset and migration safety. 57 tests passing on PostgreSQL 17 with Ruff and strict mypy clean. Implementation still marked in progress: a defined debt PR (tenant-schema provisioner and per-tenant migration runner, public statement-catalogue construction, multi-capability context issuance, the execution_id rename with migration 002, and required correlation identifiers) must land before M02 implementation. |
| M02 — Event and Operation Foundation | Requirements v1.0, Technical Design v0.3 and ADR-011 accepted; the OI-007 seed catalogue is frozen. Implementation not started and gated on the M01 debt PR. Remaining production gates OI-005, OI-006, OI-009 and OI-010 are recorded in the tracker. |
| M03 – M12 | Not started. No design, ADR or implementation. |
| Legacy prototype | src/haloflow/ contains roughly 4,000 lines of Python. Beyond M01 (about 770 lines of source plus 1,200 lines of tests and a 300-line migration), there is an earlier prototype layer: an athenahealth adapter, Notifyre fax and Stedi eligibility clients, a scheduler, and first-pass service and router code for all four Phase 1 workflows. It predates the M01 architecture, sits outside CI lint and type scope, and carries 32 known Ruff findings. It is valuable as design knowledge and as demo material; it is not production code. |
| Process discipline | Requirements → architecture → unit test cases → alignment → code, with ADRs recorded and independent security review. This is a high-assurance process. It is appropriate for PHI work and it is slower per module than ordinary application development; the estimates below assume it continues. |

# 6. Development Estimate

## 6.1 Basis and assumptions — read before using these numbers

- Estimates are per module, following the existing M01–M12 plan and its recommended order.

- An engineering week means roughly 40 focused hours. Calendar time is derived separately in §6.3.

- Each module figure includes that module’s detailed design, ADR work, unit test cases and implementation, per the established process — not implementation alone.

- AI-assisted development is assumed throughout. Integration work, compliance work and real-world edge cases compress far less than application code.

- One developer assumed.

- Excluded: sales and marketing time, clinic onboarding labour, and support of live clinics. Those are real costs, tracked separately in §2.

- Ranges are wide deliberately. They should be re-cut per module at that module’s design freeze, when the scope is actually known.

## 6.2 Estimate by module

| Module | Eng-weeks | Notes and main uncertainty |
| --- | --- | --- |
| M01 debt PR | 1.5 – 3 | Five defined items, already specified and approved as decisions B1–B8/F1. Lowest uncertainty in the plan. Gates M02. |
| M01 production readiness | 3 – 6 | Legacy module migration behind M01, production identity claims and provisioning, reliability and performance evidence, PHI-safe telemetry, runbooks. Can partly run in parallel with later modules. |
| M02 — Event and Operation Foundation | 4 – 7 | Design is complete and dense: six new shared tables, four-identifier model, event contracts, replay and reconciliation. Implementation risk is moderate because the design work is already done. |
| M03 — Webhook Inbox and Worker Runtime | 3 – 5 | HMAC verification, encrypted durable inbox, atomic claiming, leases, retries, reclaimer. |
| M04 — Tenant and Provider Routing | 2 – 4 | Registries and resolution; smallest module in the middle band. |
| M05 — Work and Error Queues | 3 – 5 | Queue states, assignment, SLA, escalation, permissions. Feeds the staff-facing surface. |
| M06 — Outbound Operation and Batch Runtime | 4 – 6 | Leases, fencing, provider idempotency, indeterminate outcomes, reconciliation. Conceptually the hardest reliability work in Phase 1. |
| M07 — SMS Messaging and Consent | 3 – 5 | Prototype exists. Consent history and STOP/START handling are compliance-sensitive. External messaging registration runs in parallel (§7). |
| M08 — Fax Processing | 5 – 8 | Largest workflow module: classification and OCR, patient matching, per-tenant storage, credential broker, retention and deletion gates, delivery tracking. |
| M09 — Eligibility and Visit Readiness | 5 – 8 | X12 270/271 normalisation, clearinghouse adapter, deterministic exceptions, EMR write-back. Prototype exists against Stedi. Per-payer enrolment is external (§7). |
| M10 — Clinic Workspace and Operational APIs | 5 – 9 | The staff-facing product surface, including the demo’s queue view. Widest range because the interface scope is not yet specified. |
| M11 — Observability and Support Operations | 3 – 5 | Cross-cutting; the tracker correctly recommends building it incrementally from M01 rather than at the end. Shown as a total, spread across the programme. |
| Phase 1 total (M01 debt → M11) | 42 – 71 | Approximately 1,700 – 2,850 focused engineering hours. |
| M12 — Governed Intelligent Layer | 8 – 14 | Tier 3 and beyond. Excluded from the Phase 1 total; listed for planning only. |

## 6.3 Milestones and calendar time

| Milestone | Eng-weeks | Includes |
| --- | --- | --- |
| D1 — Demo ready to show clinics | 2 – 5 | Built on the legacy prototype and mock adapters rather than on the M-module stack, so it does not sit behind M02–M11 and can run in parallel. Includes the scenario in §3, the deliberate exception case, a synthetic document and payer-response set, and re-skinning support. |
| P1 — First workflow live at one clinic | 30 – 52 | M01 debt and readiness, M02–M06, one workflow module, a minimum M10 surface, and the M11 slice needed to operate it safely. |
| P2 — All four workflows live (Phase 1 complete) | 42 – 71 | Through M11. |

Calendar time depends entirely on hours available per week, which is the largest single variable in this plan:

| Focused hours per week | D1 — demo | P1 — first workflow live | P2 — Phase 1 complete |
| --- | --- | --- | --- |
| 10 hrs | 2 – 5 months | 28 – 48 months | 39 – 65 months |
| 20 hrs | 1 – 2.5 months | 14 – 24 months | 19 – 33 months |
| 40 hrs | 2 – 5 weeks | 7 – 12 months | 10 – 16 months |

Observed pace as a cross-check: roughly the month of August 2026 produced the M01 implementation (with the debt PR still outstanding) plus the complete M02 design, ADR-011 and the frozen OI-007 catalogue — about four to seven engineering weeks of the plan above. If that pace is sustained, Phase 1 lands in the region of nine to fifteen months. If it halves, eighteen to thirty months. Recording actual hours per week for a few weeks would tighten this estimate more than any further analysis.

If the Phase 1 horizon is unacceptable, the available levers are: increase hours per week; reduce the first clinic’s live scope to fewer workflows while still demonstrating all four in the demo; narrow the M10 interface scope; or reduce the assurance process for non-PHI paths. The last of these should be considered carefully and probably rejected.

## 6.4 Why the first workflow costs what it does

The P1 figure is the one most worth challenging, so its composition is set out here in full.

| Component | Eng-weeks | Category |
| --- | --- | --- |
| M01 debt PR | 1.5 – 3 | Foundation |
| M01 production readiness (legacy migration, identity, telemetry, runbooks) | 3 – 6 | Foundation |
| M02 — Event and Operation Foundation | 4 – 7 | Foundation |
| M03 — Webhook inbox and worker runtime | 3 – 5 | Foundation |
| M04 — Tenant and provider routing | 2 – 4 | Foundation |
| M05 — Work and error queues | 3 – 5 | Foundation |
| M06 — Outbound operation and batch runtime | 4 – 6 | Foundation |
| One workflow module (M07, the least expensive of the four) | 3 – 5 | Workflow |
| Minimum M10 staff-facing surface | 3 – 6 | Foundation |
| M11 slice needed to operate it safely | 3 – 5 | Foundation |
| Total | 30 – 52 | — |

The workflow itself accounts for only three to five weeks. Roughly 85 per cent of the figure is infrastructure that must exist before any workflow can run, and that ordering is not an assumption imposed here — it follows the dependency register in the module tracker, where M07 depends on M03, M04, M05 and M06, which in turn depend on M01 and M02. Seven modules sit ahead of the first workflow by design.

The reason is a deliberate architectural choice already taken: M01 is tenant isolation, and the programme builds a multi-tenant, PHI-grade platform first and the workflows last. This front-loads cost onto the first clinic and makes every subsequent clinic cheap. It is the decision that avoids building a single-clinic prototype and then rewriting it into a product.

If the near-term goal were one pilot clinic rather than a sellable multi-tenant service, several components could be reduced to pilot grade: M04 is largely degenerate with a single tenant; M06 is sized for concurrency and volume that one clinic may not generate initially; parts of M01 production readiness concern operating a service rather than running one pilot; and the M11 slice could be thinner. That could plausibly bring P1 to roughly 20–35 engineering weeks.

Each of those reductions is deferred work that would have to be repaid before the second clinic, and avoiding precisely that debt is why M01 exists. The trade is recorded here rather than recommended. The more useful observation is that the demo (D1) requires none of this foundation, so contact with clinics need not wait on P1 at all.

# 7. External Enablement — often the real critical path

These items consume calendar time regardless of development speed, and several block go-live. Durations below are planning placeholders to be confirmed with each vendor and payer; they are not verified figures.

| Item | Planning allowance | Notes |
| --- | --- | --- |
| Cloud hosting BAA | Days | Self-serve. |
| BAA with the clinic | Days – 2 weeks | Required before any PHI is touched. |
| Cloud fax vendor and BAA | 1 – 2 weeks | Clinic must already be on digital fax, or migration comes first. |
| Messaging registration (A2P brand and campaign) | Weeks | Healthcare-related campaigns can attract additional review. Confirm current timelines with the provider. |
| Clearinghouse trading-partner enrolment | Weeks per payer | Per-payer paperwork requiring clinic signature. Frequently the slowest item, and it repeats for every new payer. |
| EMR production API access | To be confirmed | A sandbox adapter already exists. What is not yet established is production access terms, cost, and whether each customer practice requires its own approval and how long that takes. This is the largest scheduling unknown and should be researched before it becomes blocking. |

Planning consequence: for several workflows the enablement track can take longer than writing the code. Enrolment and approval work should start in parallel with M02–M06 rather than waiting for a workflow module to be code-complete.

# 8. Principal Risks

| Risk | Position |
| --- | --- |
| Commercial, not technical | Technical risk is comparatively low and the architecture work is serious. What is unproven is whether these clinics pay enough to cover turnkey delivery, and whether they can be reached repeatably. Neither is resolved by further architecture work. |
| Long build before outside signal | Phase 1 is a long programme for one developer. The demo (D1) is the mechanism that produces outside evidence long before P2, does not sit behind the module stack, and should be shown as early as it is presentable. |
| Onboarding labour is unbounded until measured | Turnkey delivery moves setup cost onto HaloFlow. Until measured on a real clinic it is unknown whether the subscription recovers it. Measure on clinic #1. |
| Founder credibility on a multi-year promise | A clinic buying the end state from a small team carries delivery risk. The phased rollout with free setup is the mitigation — the clinic can stop after the first workflow having lost nothing — and it should be stated explicitly in the pitch rather than left unaddressed. |
| Per-clinic configuration drift | Mitigated by maintaining a recommended default rollout order and deviating only for a stated reason. |
| Problem evidence is currently secondhand | Understanding of clinic pain derives from one practice via a personal connection, without formal discovery interviews. The demo conversations with local clinics are the first independent evidence and should be treated as such. |
| Assurance process versus schedule | The design-first, ADR-recorded, security-reviewed process is right for PHI and is a genuine asset. It is also the main reason the per-module estimates are what they are. This is a deliberate trade and should not be quietly abandoned under schedule pressure. |

# 9. Next Actions

- Record the EMR decision explicitly, rather than leaving athenahealth implicit in the adapter code, and note the pilot-clinic implication in §2.

- Confirm production EMR API access terms, cost, per-practice approval requirements and onboarding time.

- Land the M01 debt PR; it gates M02 implementation.

- Decide the disposition of the legacy prototype layer: reference spike, or code to migrate behind M01.

- Align client and investor materials with the roadmap on approval gates; reframe autonomous-execution language.

- Build the demo (D1) to the scope in §3, including the deliberate exception case, on the prototype and mock adapters so it does not wait on the module stack.

- Assemble a synthetic document and payer-response set that can be re-skinned per prospect.

- Identify local clinics to show the demo to, and prepare the observation list in §3.4.

- Begin external enablement research — messaging registration and clearinghouse enrolment — so those timelines are known before they block anything.

- Record actual focused hours per week for a few weeks, to tighten §6.3.

- From the first clinic onward, record hours spent on onboarding.

Prepared for internal discussion — Halo Holdings Track B planning. Estimates are planning figures, not commitments; re-cut each module at its design freeze.